Secondary Planning

Post-M5 Corrected Research Roadmap and Project Governance Record

An Active-Learning and Finite-Element Framework for Uncertainty-Aware Prediction of Defect-Sensitive Mechanical Properties in Particle-Reinforced Composites.

| Research route | Simulation + Machine Learning only |
| --- | --- |
| Laboratory experiments | None |
| Revision | Post-M5 alignment revision |
| Revision date | 9 August 2026 |

Status: Approved planning correction after the formal closure of M5.

# 1. Executive Decision

The project remains scientifically viable and the work completed through M5 is retained as valid. The post-M5 alignment audit identified a roadmap-order drift rather than invalid research. M4 and M5 are therefore preserved as useful inserted foundation milestones.

The project will NOT proceed directly from M5 into machine learning. The missing random-microstructure, void-defect, RVE, homogenization-boundary-condition, stochastic-variability, and final dataset stages must be completed first.

| Decision | Approved interpretation |
| --- | --- |
| M0-M5 | Remain completed; no renumbering or repetition. |
| M4-M5 | Inserted parametric/batch-pipeline foundation; they do not replace random-microstructure or defect milestones. |
| M5 dataset | Reclassified conceptually as D0-PB, a deterministic perfect-bonding centered-single-inclusion baseline. |
| Next scientific milestone | M6 - Multiple/Random-Particle Microstructure Foundation. |
| ML readiness | Final research ML is not ready to start until the corrected physics/data milestones are completed. |

This Secondary Planning record supplements the original Project 01 plan. The original plan remains the historical scope record.

# 2. Validated State Through M5

| Milestone | Description | Status |
| --- | --- | --- |
| M0 | Software and development environment | 100% COMPLETE |
| M1 | FEM fundamentals and homogeneous validation | 100% COMPLETE |
| M2 | First single-particle composite model | 100% COMPLETE |
| M3 | Mesh Convergence and Composite Verification | 100% COMPLETE |
| M4 | Parametric RVE and sampling foundation | 100% COMPLETE |
| M5 | Initial perfect-bonding FEM dataset generation | 100% COMPLETE |

## 2.1 M5 closure record

M5 produced a validated batch-execution and deterministic aggregation workflow for the locked 60-case perfect-bonding Latin-hypercube design.

All 60 FEM cases completed successfully; zero failed cases.

All FEM verification suites passed for the 60 cases.

Raw per-case JSON records and runtime logs remain local runtime artifacts and are ignored by Git.

The validated aggregate is tracked in Git and was reproduced byte-for-byte before M5 closure.

M5 closure commit: 5914bf50108c042019303ece09552768faeeb977

Documentation-dependency checkpoint before generation of this record: 05c5fc7e9d7315c6aaa48af78c9290319f1a0b6b

# 3. D0-PB Baseline Dataset Interpretation

The file results/processed/07_m5_initial_fem_dataset.csv is retained as a valuable research artifact, but it must not be treated as the final defect-sensitive stochastic dataset.

Its formal role from this planning revision onward is D0-PB: the validated perfect-bonding, centered-single-inclusion parametric baseline dataset.

| Property | Validated value |
| --- | --- |
| Formal interpretation | D0-PB baseline dataset |
| Geometry class | Centered single circular inclusion; no defect |
| Interface | Perfect bonding |
| Cases | 60/60 successful |
| Failed FEM cases | 0 |
| Aggregate rows | 60 |
| Aggregate columns | 45 |
| Effective modulus range | 1051.948603727062 to 1589.3874813628656 |
| Effective Poisson response range | 0.21573865543142967 to 0.3863453188926385 |
| Aggregate file | results/processed/07_m5_initial_fem_dataset.csv |
| Aggregate SHA-256 | e48e9eb731b6e13eb15b33ab643722a9d72e8bdb933bf24d9c1c3847776c17d1 |

## 3.1 Permitted uses of D0-PB

Regression testing of the FEM-to-dataset pipeline.

Baseline surrogate-method development and debugging.

Comparison against later stochastic/defect microstructures.

Verification of data schemas, preprocessing, and ML infrastructure.

A deterministic reference demonstrating that parameterized perfect-bonding FEM automation works.

## 3.2 Prohibited interpretation

D0-PB must not be used to support final claims about void defects, random particle arrangements, microstructure variability, OOD behavior, uncertainty reliability, or active learning efficiency.

# 4. Scientific Work Still Required Before Final ML

## 4.1 Multiple/random-particle microstructures

The present FEM baseline uses one centered circular particle. The final research problem still requires stochastic multi-particle configurations.

## 4.2 Circular void defects

No defect is present in D0-PB. Circular voids remain the planned Version-1 defect representation.

## 4.3 RVE-size/statistical representativity

M3 established mesh convergence, but mesh convergence and RVE representativity answer different questions. A stochastic RVE size study is still required.

## 4.4 Final homogenization boundary conditions

The existing displacement boundary conditions remain valid for the verified baseline problem, but random-position production data must not be generated at scale until the final homogenization BC/PBC strategy has been verified.

## 4.5 Defect-sensitive stress target

Raw local stress extrema remain diagnostics only. A more robust stress-concentration indicator must be defined and mesh checked before becoming a primary ML response.

## 4.6 Repeated microstructure realizations

Multiple seeds are required to distinguish variation caused by microstructure realization from uncertainty caused by the surrogate model.

## 4.7 Final provenance and failure schema

The production stochastic dataset should preserve case ID, physical parameters, random seed, geometry status, mesh status, solver status, element count, runtime, failure reason, and output provenance.

## 4.8 Broader physics validation

Random-RVE convergence, void-related physical trend checks, appropriate theoretical comparisons, and selected published numerical comparisons remain future validation tasks.

# 5. Corrected Future Roadmap: M6-M14

The following roadmap is the accepted continuation path. Existing milestone numbers M0-M5 remain unchanged.

| Milestone | Name | Primary purpose | Completion gate |
| --- | --- | --- | --- |
| M6 | Multiple/Random-Particle Microstructure Foundation | Develop a reproducible multi-particle geometry generator with stored random seeds, overlap prevention, minimum-spacing rules, particle-size variability, and random/clustered arrangements. | Reproducible geometry generation and validity checks pass; invalid or unmeshable geometries are explicitly recorded rather than disappearing silently. |
| M7 | Circular Void Defects and Defect-Sensitive Response Definition | Introduce circular voids as the Version-1 defect model and define a robust defect-sensitive stress-concentration output. | Void geometries mesh and solve reliably; the defect-sensitive stress target is physically interpretable and its mesh sensitivity has been assessed. |
| M8 | RVE-Size Study, Homogenization BC/PBC Verification, and Final Target-Mesh Verification | Separate statistical RVE representativity from element-level mesh convergence, verify the final homogenization boundary conditions, and establish the production mesh policy for the stochastic defect simulations. | RVE-size behavior is quantified across realizations; the final boundary-condition strategy is verified; the selected mesh is adequate for the final primary targets. |
| M9 | Final Parameter-Space Lock and Stochastic Pilot Dataset | Lock the final microstructure/defect parameter space, seed policy, result schema, provenance fields, and execute a limited pilot before expensive production runs. | Pilot runs demonstrate an end-to-end reproducible pipeline, failure reporting, runtime feasibility, and physically sensible parameter ranges. |
| M10 | Main Quality-Controlled FEM Simulation Database | Generate the principal stochastic FEM database using multiple microstructure realizations per relevant parameter condition. | The database is quality controlled, reproducible, provenance complete, and suitable for leakage-safe ML experiments. |
| M11 | Baseline Machine-Learning Models and Grouped Validation | Train interpretable conventional surrogate models using grouped splits that prevent closely related microstructures from leaking between training and validation data. | Baseline model comparison is reproducible and reported with appropriate regression metrics and physical sanity checks. |
| M12 | Active Learning versus Random Sampling | Run uncertainty-guided active learning and compare it against random acquisition under equal FEM simulation budgets. | The study can quantify whether active learning reduces prediction error or improves data efficiency relative to the random baseline. |
| M13 | Uncertainty Calibration, Variability, and OOD Testing | Separate microstructure variability from model uncertainty, evaluate uncertainty calibration, and perform deliberate out-of-distribution tests. | Prediction uncertainty is quantitatively evaluated rather than merely displayed, and unfamiliar regimes are explicitly tested. |
| M14 | Final Analysis, Ablations, Figures, and Manuscript | Consolidate scientific findings, limitations, ablations, final figures/tables, reproducibility records, and manuscript-ready results. | The final claims are supported by traceable simulations, validated ML experiments, uncertainty evidence, and a clean reproducible repository. |

# 6. Baseline Physics and Terminology Guardrails

The assumptions below describe the validated baseline through M5. They must not be silently altered.

Two-dimensional computational representation.

Small-strain linear elasticity.

Plane-stress formulation through M5.

Isotropic matrix and isotropic reinforcing particle materials.

Perfect matrix-particle bonding through M5.

Normalized RVE width = 1.0 and height = 1.0.

Centered particle for the D0-PB baseline.

Matrix Young's modulus = 1000.0 for the D0-PB baseline.

Prescribed x displacement = 0.01 for the D0-PB baseline.

Production mesh used for D0-PB = 0.02048.

Future changes such as stochastic particle placement, circular voids, or PBCs must occur only inside their explicitly announced milestones and must be separately verified.

## 6.1 2D fraction terminology

For this two-dimensional model, use 'particle area fraction' or '2D particle fraction' when describing the simulated reinforcement fraction. Avoid presenting it as a directly measured three-dimensional particle volume fraction.

## 6.2 Local stresses

Local stress extrema remain diagnostic quantities. M3 showed that some extrema are more mesh sensitive than the global effective properties. They are not automatically accepted as final ML targets.

# 7. ML, Active-Learning, and Uncertainty Guardrails

1.  Do not treat D0-PB as the final defect-sensitive research dataset.

2.  Do not begin final surrogate claims before the stochastic microstructure and defect physics are implemented and validated.

3.  Use grouped/leakage-safe validation once multiple related microstructure realizations exist.

4.  Begin with conventional tabular baselines rather than neural networks unless later evidence justifies additional complexity.

5.  Compare active learning with random selection using equal FEM simulation budgets.

6.  Evaluate uncertainty calibration quantitatively and include deliberate out-of-distribution tests.

## 7.1 Planned primary effective-property targets

Effective axial modulus.

Effective Poisson response.

A robust defect-sensitive stress-concentration indicator, only after M7 defines and verifies it.

# 8. Repository and Milestone Governance

1.  Original Project 01 remains the initial project plan and historical scope record.

2.  Secondary Planning is the authoritative post-M5 roadmap correction; it supplements rather than deletes the original plan.

3.  M0-M5 remain completed and are not renumbered or repeated.

4.  Every major milestone transition requires an explicit completion summary, next-milestone goal, progress state, and user confirmation.

5.  Research work continues strictly one concrete terminal step at a time, with output verification before continuation.

6.  For every meaningful validated repository unit: inspect changes, stage only intended paths, run staged safety checks, commit, push to origin/main, verify HEAD equals origin/main, and finish clean.

7.  PROJECT_STATUS.md should be maintained as a concise repository checkpoint so roadmap state is recoverable independently of chat memory.

## 8.1 Required persistent project records

| Record | Purpose |
| --- | --- |
| Original Project 01 planning | Historical initial scope and research intent. |
| docs/Secondary_Planning.docx | Formal approved post-M5 roadmap correction and scientific planning record. |
| PROJECT_STATUS.md | Concise current milestone, latest validated checkpoint, next step, assumptions, and Git synchronization state. |
| Git/GitHub history | Version-controlled evidence of validated implementation and planning decisions. |

# 9. Immediate Project State and Next Gate

At the time of this Secondary Planning revision, M0-M5 are formally complete and M6 has not started.

| Item | State |
| --- | --- |
| M0-M5 | 100% COMPLETE |
| Project-plan alignment audit | COMPLETE |
| Secondary Planning roadmap | APPROVED; repository documentation in progress |
| Final defect-sensitive stochastic dataset | NOT YET GENERATED |
| Random microstructures | NOT YET IMPLEMENTED |
| Circular void defects | NOT YET IMPLEMENTED |
| Final research ML phase | NOT READY TO START |
| Next major milestone | M6 - Multiple/Random-Particle Microstructure Foundation |

M6 must begin only after this planning/documentation checkpoint has been generated, validated, committed, pushed, and the user explicitly confirms the M6 transition.

# 10. Source Basis for This Secondary Plan

This planning record was prepared by reconciling the original Project 01 research plan with the validated implementation history through M5, the Project 02-04 continuation records, the repository state, and the explicitly approved post-M5 alignment discussion.

Where the execution order differed from the original plan, the completed work was preserved when scientifically valid and the missing original-scope requirements were restored to the future roadmap rather than silently discarded.